Copilot Agents Hack-a-Thon

Facilitator Guide

Inspire Brands  |  March 31, 2026

John Rea  |  Sr CSA - Copilot  |  Microsoft

How to use this guide Read this guide end-to-end before the event. Bring a printed copy on the day and keep it next to your laptop during the build phase. Priority sections: Section 4 (Run of Show) and Section 5 (Build Phase Coaching).

# Table of Contents

Table of Contents	2

Section 1: Event Overview	4

What Success Looks Like	4

Attendee Profile	4

Section 2: Pre-Event Checklist	5

2 Weeks Before	5

1 Week Before	5

Day Before	5

Section 3: Day-of Logistics	7

Room Setup (Arrive by 8:00 AM)	7

AV Setup	7

Technical Setup — Your Laptop	7

Section 4: Run of Show — Minute by Minute	8

Section 5: Build Phase Coaching Guide	9

Check-in Schedule	9

Coaching Prompts	9

Common Technical Issues	9

Section 6: Inspire Brands Agent Scenarios	11

Scenario 1 — Franchise Daily Ops Agent	11

Scenario 2 — Guest Recovery Agent	11

Scenario 3 — New Hire Onboarding Agent	11

Scenario 4 — Inventory Reorder Alert Agent	12

Scenario 5 — Campaign Content Agent	12

Scenario 6 — Food Safety Audit Agent	13

Section 7: FAQ & Troubleshooting	14

Q: What if an attendee does not have a Microsoft 365 Copilot license?	14

Q: What if Copilot Studio is slow or unresponsive?	14

Q: What if a team finishes building before 3:00 PM?	14

Q: What if a team is completely stuck?	14

Q: What if attendees are skeptical about AI?	14

Q: What if the WiFi fails completely?	14

Q: What if no one wants to go first in demos?	14

Q: What if a team's agent does not work during the demo?	14

Section 8: Post-Event Follow-Up	15

Within 24 Hours	15

Within 48 Hours — Follow-Up Email Template	15

Engagement Logging	15

# Section 1: Event Overview

This document is your complete guide for facilitating the Copilot Agents Hack-a-Thon at Inspire Brands on March 31, 2026. It is designed for a first-time facilitator delivering this engagement.

## What Success Looks Like

- Every attendee has hands-on experience building a Microsoft 365 Copilot agent

- Every team demos a working proof-of-concept by 4:30 PM

- Inspire Brands leaves with 2–3 specific agent scenarios ready to pilot

- You have a clear next-step proposal for Inspire Brands within 48 hours

## Attendee Profile

| Attribute | Details |
| --- | --- |
| Expected roles | IT leaders, business analysts, franchise operations, marketing, HR |
| Technical level | Mixed — some very technical (IT/dev), most business users |
| Expected headcount | 10–20 attendees (optimal for hackathon format) |
| License requirement | Every attendee MUST have a Microsoft 365 Copilot license |
| Event format | 200-level intermediate, guided, hands-on, full day on-site in Boston |

# Section 2: Pre-Event Checklist

## 2 Weeks Before

| Task | Owner | Done |
| --- | --- | --- |
| Confirm all attendees have Microsoft 365 Copilot licenses | John Rea + Inspire IT | [ ] |
| Confirm Copilot Studio access is enabled for attendees (included with M365 Copilot license — no separate trial needed) | Inspire Brands IT | [ ] |
| Send attendee pre-read: What are AI Agents in M365? (Microsoft Learn) | John Rea | [ ] |
| Confirm room: full-day, team pod seating for 4-5 per table | Inspire Brands | [ ] |
| Confirm AV: projector/screen, HDMI or USB-C adapters | Inspire Brands | [ ] |
| Request strong WiFi credentials (full M365 access, not guest) | Inspire Brands IT | [ ] |
| Plan backup connectivity: personal hotspot as failover | John Rea | [ ] |
| Print participant workbooks (1 per attendee) | John Rea | [ ] |
| Prepare sample SharePoint site with Inspire Brands docs for Exercise 2 | John Rea | [ ] |
| Pre-load Agent Builder and Copilot Studio in browser tabs and test login | John Rea | [ ] |
| Confirm catering: breakfast, lunch, afternoon snacks | Inspire Brands | [ ] |

## 1 Week Before

| Task | Owner | Done |
| --- | --- | --- |
| Send calendar invite: address, parking, WiFi info, agenda | John Rea | [ ] |
| Test full exercise flow on your own laptop end-to-end | John Rea | [ ] |
| Prepare 2–3 sample starter agents for teams who get stuck | John Rea | [ ] |
| Test Copilot Studio loads correctly with attendee tenant (not your own) | John Rea | [ ] |
| Prepare post-event follow-up email (template in Section 8) | John Rea | [ ] |

## Day Before

| Task | Owner | Done |
| --- | --- | --- |
| Confirm room setup time — plan to arrive 45 minutes before attendees | John Rea | [ ] |
| Charge devices; pack USB-C hub, power brick, presentation clicker | John Rea | [ ] |
| Pre-download: slide deck, workbooks, facilitator guide (offline backup) | John Rea | [ ] |
| Print WiFi credentials sheet (one per table) | John Rea | [ ] |
| Test laptop connectivity to room AV system | John Rea | [ ] |
| Pack printed workbooks, whiteboard markers, sticky notes | John Rea | [ ] |

# Section 3: Day-of Logistics

## Room Setup (Arrive by 8:00 AM)

- Tables in pods of 4–5 chairs each — team-based seating, not classroom rows

- Facilitator station at front: laptop + projector + whiteboard access

- Each table: printed workbooks, sticky notes, markers, WiFi credentials card

- Power strips under or near each table if possible

## AV Setup

- Connect laptop to projector — test HDMI and USB-C dongle

- Pre-advance slides to Slide 2 (Agenda) as welcome screen while people arrive

- Backup plan: if projector fails, share deck link so attendees view on laptops

## Technical Setup — Your Laptop

- Browser tabs pre-loaded: microsoft365.com, copilotstudio.microsoft.com, Agent Builder

- Slide deck open in Presenter Mode (notes visible only on your screen)

- This facilitator guide open in a second window

- Backup: deck saved to OneDrive AND downloaded locally

WiFi Warning Critical: Verify you can access microsoft365.com and copilotstudio.microsoft.com on the room WiFi BEFORE attendees arrive. If guest WiFi blocks Microsoft 365, escalate to Inspire Brands IT immediately — this is a day-of blocker. Switch to personal hotspot without hesitation if needed. Test it in advance.

# Section 4: Run of Show — Minute by Minute

| Time | Dur. | Activity | Facilitator Actions & Talking Points |
| --- | --- | --- | --- |
| 8:30–9:00 AM | 30 min | Registration & Networking | Welcome attendees personally at the door. Ask: "What is your role at Inspire Brands?" Icebreaker optional: sticky note with one task that wastes your time. Keep energy warm: "Today is hands-on and fun." |
| 9:00–9:30 AM | 30 min | Welcome & Scene Setting (Slides 1–3) | Intro: name, CSA role, Microsoft. Cover agenda — emphasize 2.5 hrs building time. Share 3 outcomes. Quick intros: name + role + one word describing what they hope to build. "Safe space. No wrong answers. We learn by building." |
| 9:30–10:30 AM | 60 min | Educational Session (Slides 4–8) | Slide 4: A chatbot answers questions, an agent takes action. Slide 5: Most teams use Declarative column. Slide 6: Tie value to Inspire Brands. Slide 7: Raise hand for scenario keeping you up at night. Slide 8: M365 security boundary. |
| 10:30–10:45 AM | 15 min | Break | Circulate. Ask informally: "What scenario are you leaning toward?" Note teams needing extra hackathon support. |
| 10:45–11:45 AM | 60 min | Hands-On Exercises (Slides 9–12) | Ex 1 (15 min): Pre-built agent in Teams. Ex 2 (30 min): Declarative agent in Agent Builder — live-demo UI for 3 min first. Ex 3 (20 min): Orient in Copilot Studio. Walk the room constantly. Ask: "What are you trying to build?" |
| 11:45 AM–12:30 PM | 45 min | Lunch | Plant hackathon seeds. Ask each table: which scenario resonates? Ensure teams are naturally forming before lunch ends. Quietly introduce anyone without a team. |
| 12:30–1:00 PM | 30 min | Hackathon Kickoff (Slides 13–16) | High energy: Hackathon starts now. Rules: every team demos, live only, 5 min. Teams claim a scenario. Show Design Canvas — 10 min to fill out BEFORE building. Circulate and review each canvas. RED FLAG: team still arguing about scenario at 12:55 PM — assign one. |
| 1:00–3:30 PM | 150 min | Build Phase | Check in at 1:10, 1:30, 2:15, 3:00. Ask: "What is your agent doing right now?" At 3:00 PM: STOP building, prepare demo. See Section 5 for coaching prompts. |
| 3:30–3:45 PM | 15 min | Break | Remind teams: Demo in 15 minutes. Practice 30-second intro. Help any team in crisis with their demo flow. |
| 3:45–4:30 PM | 45 min | Team Demos (Slides 17–19) | Use visible 5-min timer. Most confident team volunteers first. After each: "One thing you liked?" Keep Q&A under 90 sec. Group vote for favorite after all demos. Recognize winner. |
| 4:30–5:00 PM | 30 min | Wrap-Up & Next Steps (Slides 20–21) | Recap top 2–3 scenarios. Present specific next-step recommendation. Get a named owner for follow-up. Capture whiteboard photos. Exchange contact info. |

# Section 5: Build Phase Coaching Guide

## Check-in Schedule

| Time | Check-in Goal |
| --- | --- |
| 1:10 PM | Quick round — every team has a finalized canvas (not still planning) |
| 1:30 PM | Deeper check-in: "What is your agent doing right now?" (not "How are you doing?") |
| 2:15 PM | "Are you on track for a demo at 3:45?" Nudge any team to narrow scope if needed |
| 3:00 PM | "Stop building. Start preparing your demo." Enforce this firmly. |

## Coaching Prompts

### When a team is stuck

- "If I were the user, what would I type to start a conversation with your agent?"

- "What is ONE thing your agent absolutely must do? Just build that first."

- "What is the simplest version of this that still demonstrates value?"

### When a team is overcomplicating

- "What if your agent only did one specific action? Would that still be useful?"

- "A narrow scenario done well is worth more than an ambitious one half-built."

### When a team finishes early

- "Can you add a second knowledge source to improve accuracy?"

- "What questions is your agent getting wrong? Fix that with better instructions."

- "Can you improve the demo flow so value is obvious in the first 30 seconds?"

## Common Technical Issues

| Issue | Likely Cause | Resolution |
| --- | --- | --- |
| Agent Builder not loading | License not provisioned or wrong tenant | Check microsoft365.com/admin; try Edge browser |
| Knowledge source not returning results | Still indexing (2–5 min) | Wait and retry; have a fallback document ready |
| Copilot Studio loading slowly | Browser cache or VPN | Clear cache, disable VPN, try incognito mode |
| Agent giving wrong answers | Instructions too vague | Help refine system prompt to be more specific |
| Cannot log into Copilot Studio | Wrong tenant or no license | Confirm tenant URL; check license in M365 Admin |
| WiFi dropping | Guest network blocking M365 | Switch to personal hotspot immediately |
| Team completely stuck | Scope too broad, no clear user | Name ONE user with ONE problem. Build for that person only. |

Most Common Hackathon Failure Mode The most common reason teams fail to demo is trying to build too much. A working agent that does ONE thing well beats a broken agent that tries everything. If a team has more than 3 topics in Copilot Studio at 2:00 PM, intervene.

# Section 6: Inspire Brands Agent Scenarios

Use this section as your reference when coaching teams during the hackathon. Each scenario includes a build guide with specific starting instructions.

## Scenario 1 — Franchise Daily Ops Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Easy |
| Agent Type | Declarative Agent (Agent Builder) |
| User Persona | Regional franchise manager overseeing 8–15 stores |
| Knowledge Sources | SharePoint with daily ops reports, brand standards, compliance checklists |
| Key Actions | Answer KPI questions, surface compliance gaps, list open items by store |
| Expected Outcome | Save franchise managers 3–4 hrs/week; improve response to underperforming stores |

Build Guide:

System prompt: "You are a franchise operations assistant for Inspire Brands. Use the provided documents to answer questions about daily store performance. Be concise and direct." Add a SharePoint knowledge source. Test with: "Which stores had the lowest scores yesterday?" and "What are the top compliance issues this week?"

## Scenario 2 — Guest Recovery Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Medium |
| Agent Type | Custom Agent (Copilot Studio) |
| User Persona | Guest Relations specialist or store manager |
| Knowledge Sources | Guest recovery policy, brand-specific response guidelines, escalation matrix |
| Key Actions | Classify complaint type, suggest recovery action, flag escalations, draft response |
| Expected Outcome | Reduce complaint-to-resolution time from 48 hours to 4 hours across all brands |

Build Guide:

Create Copilot Studio agent with topics for each complaint category (food quality, service, wait time, order error). Each topic suggests a recovery action from policy and offers to draft a response. Advanced: connect to guest feedback API.

## Scenario 3 — New Hire Onboarding Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Easy |
| Agent Type | Declarative Agent (Agent Builder) |
| User Persona | New hourly employee or new corporate hire at any Inspire brand |
| Knowledge Sources | Employee handbook (SharePoint), benefits guide, first-week task checklist |
| Key Actions | Answer policy questions, surface required forms, first-week step-by-step guidance |
| Expected Outcome | Reduce HR onboarding support tickets by 40%; improve new hire retention |

Build Guide:

System prompt: "You help new Inspire Brands employees navigate their first 30 days. Answer only using the provided documents. Always be encouraging and clear." Test with: "What do I need to do on my first day?" and "How do I enroll in benefits?"

## Scenario 4 — Inventory Reorder Alert Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Medium |
| Agent Type | Custom Agent (Copilot Studio) |
| User Persona | Store manager or supply chain coordinator |
| Knowledge Sources | Vendor contact list, par-level thresholds document, order form templates |
| Key Actions | Recommend reorder quantities based on par levels, draft reorder email to vendor |
| Expected Outcome | Reduce out-of-stock incidents by 25%; save 2 hrs per store per week |

Build Guide:

Start declarative: upload vendor contact list and par-level doc. Instructions: recommend reorder when item is mentioned as low. Advanced: connect to inventory management API via Copilot Studio action.

## Scenario 5 — Campaign Content Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Easy |
| Agent Type | Declarative Agent (Agent Builder) |
| User Persona | Brand marketing coordinator for Arby's, Sonic, Dunkin', etc. |
| Knowledge Sources | Brand guidelines per brand, campaign examples, tone-of-voice documents |
| Key Actions | Generate social captions, promo email subject lines, in-store copy per brand voice |
| Expected Outcome | Reduce content creation time from 3 hours to 30 minutes per campaign |

Build Guide:

Instructions: "When the user specifies a brand, follow that brand tone-of-voice guidelines exactly. Always present 3 options for the user to choose from." Create one knowledge source per brand or one document with brand sections.

## Scenario 6 — Food Safety Audit Agent

| Attribute | Details |
| --- | --- |
| Difficulty | Hard |
| Agent Type | Custom Agent (Copilot Studio) |
| User Persona | Food safety manager or compliance officer |
| Knowledge Sources | FDA food safety guidelines, audit checklists, corrective action templates, incident logs |
| Key Actions | Walk through audit prep checklist, surface open corrective actions, generate summary report |
| Expected Outcome | Reduce audit prep time from 8 hours to 2 hours; reduce findings through proactive documentation |

Build Guide:

Requires Copilot Studio for multi-step workflow. Create an agent that guides through a checklist where each item is a topic. Generate a summary report at the end. Ambitious for 2.5 hours — recommend for technically strong teams only.

Facilitator Note Only assign this to teams with at least one technically strong person. It requires Copilot Studio actions and multi-topic flow design.

# Section 7: FAQ & Troubleshooting

## Q: What if an attendee does not have a Microsoft 365 Copilot license?

A: They can participate in Copilot Studio exercises (which has a trial) and team up with a licensed colleague for Agent Builder. Pair them intentionally at team formation so they are never blocked.

## Q: What if Copilot Studio is slow or unresponsive?

A: Usually a browser issue. Try: (1) clear browser cache, (2) use incognito/private mode, (3) switch from Chrome to Edge, (4) disable VPN. Edge is the most reliable browser for M365 tools.

## Q: What if a team finishes building before 3:00 PM?

A: Use coaching prompts: add a second knowledge source, improve instruction quality, practice and tighten the demo flow, or begin drafting a production deployment plan.

## Q: What if a team is completely stuck?

A: Scope is too broad. Walk them through this: "Name one person. Name one thing that person asks repeatedly. Build an agent that answers only that one thing." This always unlocks them.

## Q: What if attendees are skeptical about AI?

A: Do not argue. Say: "Your skepticism is healthy — we are going to let the demo speak for itself. Try building one thing, and then tell me what you think." Skeptics who build something often become the loudest advocates.

## Q: What if the WiFi fails completely?

A: Switch to personal hotspot immediately. If all connectivity fails: pause the build phase, run group paper-based scenario planning using the canvas, and reschedule the actual build as a virtual session within 2 weeks.

## Q: What if no one wants to go first in demos?

A: Prep a volunteer in advance — briefly ask one confident attendee over lunch if they will present first. A strong opening demo sets the tone and encourages everyone else.

## Q: What if a team's agent does not work during the demo?

A: Normalize it: "This is exactly what happens in real pilots, and it is why we demo early." Ask them to walk through what the agent is supposed to do and what they would fix. Intent and design are as valuable as a working demo in this context.

# Section 8: Post-Event Follow-Up

## Within 24 Hours

- Capture notes: top 2–3 scenarios built, team contacts, specific pain points raised

- Take photos of the whiteboard and any team canvases left behind

- Note any technical blockers for future event prep improvements

## Within 48 Hours — Follow-Up Email Template

Email Template Subject: Your Copilot Agents Hack-a-Thon — Recap & Next Steps Hi [Name], Thank you for an energizing day at the Copilot Agents Hack-a-Thon. What your teams built in 2.5 hours was genuinely impressive, and I left with a clear sense of how AI agents can create real value at Inspire Brands. Key highlights from the day: [Insert 2–3 bullet points: scenarios built, standout demos, key themes] Based on today's demos, my recommended next step is: [e.g., "AI Agents Pilot — Workforce Productivity, starting with the Franchise Daily Ops Agent"] I'd like to schedule a 30-minute call this week. Are you available [day] or [day]? John Rea ¦ john.rea@microsoft.com ¦ Senior Cloud Solution Architect, Microsoft

## Engagement Logging

| Field | Value |
| --- | --- |
| Customer | Inspire Brands |
| Engagement type | AI Agents Hack-a-Thon (200-level) |
| Outcomes to capture | Number of POC agents built, scenarios identified, next step proposed |
| CRM / MSX update | Update opportunity with next step engagement and follow-up date |
| Manager update | Send brief email to Cristi Bennett: top 3 outcomes + recommended next engagement |

Most Important Reminder Follow up within 48 hours. Hackathon momentum is powerful but fragile. Worst outcome: great demos, no follow-up, and Inspire Brands moves on without a next step. Have a specific pilot recommendation ready BEFORE you leave the room at 5:00 PM.